LONGFORD PARK SCHOOL

2022-2023

Curriculum Development plan for  Computing & iPads

| Key Targets | Actions | By whom | By When | How will performance and impact be measured? | Success Criteria Key Performance Indicators |
| --- | --- | --- | --- | --- | --- |
| 1. To further develop pupils’ independent use of technology through programming | - Assess how to involve pupils of all ages in programming and coding physical computing equipment. - Use information/training gathered from TTSA and network groups to assist in our use of technology in school. - Research safe & appropriate games that pupils can access on the computers or iPads in their free time. - Continue research into Minecraft education. – Liaise with IG about class logins etc.. Assess whether the curriculum objectives are applicable to our school. - Further research into up to date apps for the iPads. Look into apps that can be used for teaching & Learning. E.g – Geography = “Geo Challenge” app History = World History for kids app | JH/JL JH/IG JH/IG | Spring term Autumn Ongoing | Feedback from learning walk, pupil voice, feedback from teaching staff. | - Pupils throughout the school are contributing towards enhancing their programming/coding knowledge. - iPads, computer software & additional hardware is used across the curriculum on a regular basis to enhance teaching & learning. - E-safety will be addressed at least once per half term within classes. - A list of appropriate and safe games will be created and shared with all classes. |
| 2. Teaching staff to have secure subject knowledge of what they’re teaching and ensure good quality of education. | - Collect teacher assessments at the end of each term and compare with national expectations. - Scrutinise examples of work. - Examples of pupils work to be saved into organised folders and checked - Teaching Staff to share ideas amongst key stages to create bank of resources - Staff computer sessions – Drop in/Q & A’s about technology/subject topics | JH JH | Ongoing Autumn & Summer terms | Teacher assessments judged using the assessment spreadsheet on the shared drive. Assessments to be submitted to JH who will monitor on central, whole school spreadsheet. JH to check teacher assessments with evidence of pupil work. | - To improve the % of ks2 pupils that are at ARE - Folder of Staff Resources |
| 3. To improve the eco status & reliability of technology in school. | - Check all computers & IWBs are switched off at the end of each school day. - Check that iPads are all plugged in to the trolley and are charging every day. - Ensure that all faults with technology are logged straight away on the NEW system. | JH/AD JL/JH All staff | Ongoing Ongoing Ongoing | IT request log database, pupil voice, feedback from teachers regarding reliability, feedback from caretaker regarding Eco status. | - All computers will be switched off at the end of every day. - All iPads will be charged and ready for use each day. - All staff will be logging any faults or requirements using the correct system. |
| 4. To develop links within the wider curriculum to provide enrichment opportunities for pupils linked to Computing | - Use 1 of 2 computing lessons to show cross curricular links and show evidence of this in class books. - To create STEM learning opportunities for pupils | All Staff | Ongoing | Monitoring of ICT Evidence of STEM learning | - Clear evidence of cross curricular links being used in Computing |